## Schedule
https://www.smartsheet.com/try-it?trp=8792&utm_source=integrated+content&utm_campaign=/free-google-docs-templates-google-timeline-templates&utm_medium=Gantt+Chart+with+Timeline+google+sheets+8792&lpa=Gantt+Chart+with+Timeline+google+sheets+8792&lx=PFpZZjisDNTS-Ddigi3MyABAgeTPLDIL8TQRu558b7w
PROJECT TITLE
Daily Meal Planner
TEAM MEMBERS
Willy Leung, Mrinal Raj Lakkimsetty, Maheswari Adavi, Sarayu Pacca, Zhongxing "Jordan" Qin
Sprint 1
TASK | TASK | TASK | START | DUE | EXPECTED | % OF TASK | WEEK 10/2 | [6 empty] | WEEK 10/9 | [6 empty] | WEEK 10/16
ID | TITLE | OWNER | DATE | DATE | # OF DAYS | COMPLETE | W | Th | F | Sa | S | M | T | W | Th | F | Sa | S | M | T | W | Th | F | Sa | S | M | T
1 | Modify User Input Interface for Cooking Time Estimation
1.1 | Understand the code baseline structure | Jordan | 2024-10-04 | 2024-10-06 | 3 | 0%
1.2 | Design the input form prototype for user input | Jordan | 2024-10-07 | 2024-10-09 | 3 | 0%
1.3 | Build the frontend input form | Jordan | 2024-10-10 | 2024-10-12 | 3 | 0%
1.4 | passe the user' input time to the back-end database | Jordan | 2024-10-13 | 2024-10-15 | 3 | 0%
1.5 | Test the input feature to ensure it works as intended | Jordan | 2024-10-16 | 2024-10-16 | 1 | 0%
2 | Implement bug fixes to display # of plans
2.1 | Review and locate affected files | Willy | 2024-10-05 | 2024-10-07 | 3 | 0%
2.2 | Debug and fix files | Willy | 2024-10-07 | 2024-10-10 | 4 | 0%
3 | Implement a back-end database to store meal plans
3.1 | Set up and configure an AWS RDS instance (using MySQL) | Willy | 2024-10-09 | 2024-10-10 | 2 | 0%
3.2 | Write a JS file to connect to the DB using Node.js | Willy | 2024-10-10 | 2024-10-13 | 4 | 0%
3.3 | Store generated meal plans | Willy | 2024-10-13 | 2024-10-15 | 3 | 0%
3.4 | Transfer generated meal plans to DB | Willy | 2024-10-15 | 2024-10-18 | 4 | 0%
3.5 | Test the code | Willy | 2024-10-19 | 2024-10-19 | 1 | 0%
4 | Enhance plan type selection with expanded user options
4.1 | Understand the code. | Sarayu | 2024-10-05 | 2024-10-07 | 3 | 0%
4.2 | Create custom plan option in UI | Sarayu | 2024-10-08 | 2024-10-10 | 3 | 0%
4.3 | Design user input for custom days | Sarayu | 2024-10-12 | 2024-10-14 | 2 | 0%
4.4 | Basic frontend logic for custom plan | Sarayu | 2024-10-15 | 2024-10-17 | 3 | 0%
5 | Implement method to switch out food in plan
5.1 | Recode the program to fetch another food item | Mrinal | 2024-10-12 | 2024-10-18 | 7 | 0%
5.2 | Add switch out buttons to each food item in plan | Mrinal | 2024-10-13 | 2024-10-15 | 3 | 0%
6 | Implement a method for a user to save meal plans
6.1 | Create a "history" tab in the main page | Willy | 2024-10-19 | 2024-10-19 | 1 | 0%
6.2 | Display previous meal plans from the DB in this history page | Willy | 2024-10-20 | 2024-10-22 | 3 | 0%
7 | Implement a way to show calories for each food in the meal plan
7.1 | Research and select a calorie data source | Sarayu, Maheswari | 2024-10-10 | 2024-10-12 | 3 | 0%
7.2 | Display the calories on the meal page | Maheswari | 2024-10-13 | 2024-10-16 | 4 | 0%
Sprint 2
TASK | TASK | TASK | START | DUE | DURATION | % OF TASK | WEEK 10/23 | [6 empty] | WEEK 10/30
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | W | Th | F | Sa | S | M | T | W | Th | F | Sa | S | M | T
1 | Implement a method for a user to save meal plans (CONT.)
1.1 | Add delete buttons to delete past meal plans | Willy, Jordan | 2024-11-01 | 2024-11-03 | 3 | 0%
1.2 | Update the data in DB to reflect deleted data | Willy, Jordan | 2024-11-03 | 1930-11-05 | 3 | 0%
2 | Implement method to switch out food in plan (CONT.)
2.1 | Prompt user with questions to specify which food they want | Mrinal | 2024-11-01 | 2024-11-05 | 5 | 0%
3 | Enhance plan type selection with expanded user options
3.1 | Handle custom plan logic and Backend integration | Sarayu | 2024-10-23 | 2024-10-26 | 4 | 0%
3.2 | Validation and Testing | Sarayu | 2024-10-27 | 2024-10-29 | 3 | 0%
4 | Prepare for Demo on 10/30
4.1 | Review code (refactor, simplify, debug) | All teams | 2024-10-23 | 2024-10-29 | 7 | 0%
4.2 | Integrate code into Github | Willy, All teams | 2024-10-23 | 2024-10-29 | 7 | 0%
5 | Implement a way to show calories for each food in the meal plan
5.1 | Provide context for calorie counts | Sarayu, Maheswari | 2024-10-31 | 2024-11-05 | 6 | 0%
Sprint 3
TASK | TASK | TASK | START | DUE | DURATION | % OF TASK | WEEK 11/6 | [6 empty] | WEEK 11/13
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | W | Th | F | Sa | S | M | T | W | Th | F | Sa | S | M | T
1 | Implement a method for a user to save meal plans (CONT.)
1.1 | Add a confirm window for deletion (i.e. "Are you sure?") | Willy, Jordan | 2024-11-06 | 2024-11-08 | 3 | 0%
2 | Prepare for Demo on 11/13
2.1 | Review code (refactor, simplify, debug) | All teams | 2024-11-09 | 2024-11-12 | 4 | 0%
2.2 | Integrate code into Github | Willy, All teams | 2024-11-09 | 2024-11-12 | 4 | 0%
3 | Implement method to switch out food in plan (CONT.)
3.1 | Update DB to reflect food switched out in current meal plan | Mrinal, Willy | 2024-11-14 | 2024-11-18 | 5 | 0%
4 | Enhance plan type selection with expanded user options
4.1 | Improve the frontend for plan type selection. | Sarayu | 2024-11-15 | 2024-11-20 | 6 | 0%
5 | Implement a way to show calories for each food in the meal plan
5.1 | Improve the frontend of the page. | Maheswari | 2024-11-15 | 2024-11-17 | 3 | 0%
Sprint 4
TASK | TASK | TASK | START | DUE | DURATION | % OF TASK | WEEK 11/20 | [6 empty] | WEEK 11/27 | [6 empty] | WEEK 12/4
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | W | Th | F | Sa | S | M | T | W | Th | F | Sa | S | M | T | W | Th | F | Sa | S | M | T
1 | Prepare for presentation on 12/4
1.1 | Review code (refactor, simplify, debug) | All teams | 2024-11-20 | 2024-12-03 | 14 | 0%
1.2 | Integrate code into Github | Willy, All teams | 2024-11-27 | 2024-12-03 | 6 | 0%
2 | Implement a method for a user to save meal plans (CONT.)
2.1 | Implement way to view two meal plans side-by-side | Willy, Jordan | 2024-11-20 | 2024-11-25 | 5 | 0%
4 | Enhance plan type selection with expanded user options
4.1 | Review code | Sarayu, All teams | 2024-11-21 | 2024-11-25 | 5 | 0%
5 | Implement a way to show calories for each food in the meal plan
5.1 | Review code | Maheswari, All teams | 2024-11-21 | 2024-11-25 | 5 | 0%